## Sheet1
Field crew | Segment | N Bends | Weeks (2 bends per week) | person hours per week
MT | 2 | 12 | 6 | 240 | Done by November/until April | Trotlines are quick
MT | 3 | 21 | 10.5 | 240 |  | 18 hours may be feasible with 2 crews
MT | 4 | 12 | 6 | 240 |  | Gill nets - do 24 hour sets, but take a bit of time, no weights
95% of time 1 crew could do 2 bends per week,
Nebraska | 7 | 12 | 6 | 240
Nebraska | 8 | 15 | 7.5 | 240 | October 1, maybe september
Nebraska | 9 | 10 | 5 | 240 | daytimes above 32
MDC | 9 | 10 | 5 | 240
MDC | 10 | 10 | 5 | 240
USACE | 13 | 13 | 6.5 | 240 | October 1 to December, then pick up in March
USACE | 14 | 14 | 7 | 240
Age-0 during spring pulse
UB: Junish-to July, duration
LB: May run through end of september for HAMP rare to find fish in early may, Finish up sturgeon season and roll into age-0 sampling, cool summer you will see age-0 shovelnose all summer long, another peak in the fall. 3 month window, mid may June, July, August. OT04 gear avoidance after certain size fish
South Dakota won't do much
value of fish community data---valuable to state and service but limited to USACE decisions thus far
Not get age-0 from fish community data
**Biop metric---to monitor spring pulse or flow for 9 years and measure effect is reproductive output and define whether fish reporoduce or not.
** Needed to link flow to reproducing
Will need to likely address prey fish
YOY

## Sheet3
|  |  |  | Bends/week | N Crews | Weeks to complete | fallStart | fallEnd | nFallWeeks | springStart | springEnd | nSpringWeeks
Upper basin | 1 | MT | 0 | 2 | 1 | 0
| 2 | MT | 12 | 2 | 1 | 6 | 34 | 43 | 9 | 12 | 25 | 13
| 3 | MT | 21 | 2 | 1 | 10.5 | 34 | 43 | 9 | 13 | 25 | 12
| 4 | MT | 10 | 2 | 1 | 5 | 34 | 43 | 9 | 13 | 25 | 12
Inter reservoir | 5 & 6 | UFSWS-GP | 10 | 2 | 1 | 5 | 43 | 46 | 3 | 10 | 19 | 9
Lower | 7 | SD | 12 | 2 | 1 | 6 | 40 | 51 | 11 | 0 | 17 | 17
| 8 | NE | 15 | 2 | 1 | 7.5 | 40 | 47 | 7 | 3 | 16 | 13
| 9 | NE | 10 | 2 | 1 | 5 | 41 | 50 | 9 | 0 | 15 | 15
| 9 | MO | 10 | 2 | 1 | 5 | 41 | 50 | 9 | 0 | 15 | 15
| 10 | MO | 10 | 2 | 1 | 5 | 40 | 50 | 10 | 0 | 15 | 15
| 13 | ? | 11 | 2 | 1 | 5.5 | 43 | 51 | 8 | 0 | 15 | 15
| 14 | ? | 14 | 2 | 1 | 7 | 43 | 52 | 9 | 0 | 15 | 15

## 2 crews @ 2 bends per wk
Segment | Group | Bends to sample | Crews | Bends/week | Weeks to complete | Week of year (September 1 to June 1)
[6 empty] | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | MT | 12 | 1 | 2 | 6 | Week of year (September 1 to June 1) 34: x; Week of year (September 1 to June 1) 35: x; Week of year (September 1 to June 1) 36: x; Week of year (September 1 to June 1) 37: x; Week of year (September 1 to June 1) 38: x; Week of year (September 1 to June 1) 39: x; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: 4; Week of year (September 1 to June 1) 13: 4; Week of year (September 1 to June 1) 14: 4; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
3 | MT | 21 | 1 | 2 | 10.5 | Week of year (September 1 to June 1) 34: x; Week of year (September 1 to June 1) 35: x; Week of year (September 1 to June 1) 36: x; Week of year (September 1 to June 1) 37: 4; Week of year (September 1 to June 1) 38: 4; Week of year (September 1 to June 1) 39: 4; Week of year (September 1 to June 1) 40: 4; Week of year (September 1 to June 1) 41: 4; Week of year (September 1 to June 1) 42: 1; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
4 | MT | 12 | 1 | 2 | 6 | Week of year (September 1 to June 1) 34: 2; Week of year (September 1 to June 1) 35: 2; Week of year (September 1 to June 1) 36: 2; Week of year (September 1 to June 1) 37: 2; Week of year (September 1 to June 1) 38: 2; Week of year (September 1 to June 1) 39: 2; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
5&6 | UFSWS-GP | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x
7 | SD | 12 | 1 | 2 | 6 | [6 empty] | 2 | 2 | 2 | x | x | x | x | x | x | x | x | x |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
8 | NE | 15 | 1 | 2 | 7.5 | Week of year (September 1 to June 1) 40: 2; Week of year (September 1 to June 1) 41: 2; Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 47: 1; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x
9 | NE | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: 2; Week of year (September 1 to June 1) 9: 2; Week of year (September 1 to June 1) 10: 2; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
9 | MO | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: 2; Week of year (September 1 to June 1) 9: 2; Week of year (September 1 to June 1) 10: 2; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
10 | MO | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 40: 2; Week of year (September 1 to June 1) 41: 2; Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
13 | ? | 11 | 1 | 2 | 5.5 | Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 47: 1; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 51: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
14 | ? | 14 | 1 | 2 | 7 | Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 51: x; Week of year (September 1 to June 1) 52: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: 2; Week of year (September 1 to June 1) 4: 2; Week of year (September 1 to June 1) 5: 2; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: 2; Week of year (September 1 to June 1) 9: 2; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
[51 empty] | crews | crew size | Salary
[50 empty] | mt | 2 | 3 | 40000 | 324000
[50 empty] | sd | 1 | 3 | 40000 | 162000
[50 empty] | ne | 1 | 3 | 40000 | 162000
[50 empty] | mo | 1 | 3 | 40000 | 162000
[50 empty] | ?? | 1 | 3 | 40000 | 162000
0.972

## 1 crews @ 1 bends per wk
Segment | Group | Bends to sample | Crews | Bends/week | Weeks to complete | Week of year (September 1 to June 1)
[6 empty] | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | MT | 12 | 2 | 1 | 6 | Week of year (September 1 to June 1) 34: 2; Week of year (September 1 to June 1) 35: 2; Week of year (September 1 to June 1) 36: 2; Week of year (September 1 to June 1) 37: 2; Week of year (September 1 to June 1) 38: 2; Week of year (September 1 to June 1) 39: 2; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
3 | MT | 21 | 2 | 1 | 10.5 | Week of year (September 1 to June 1) 34: x; Week of year (September 1 to June 1) 35: x; Week of year (September 1 to June 1) 36: x; Week of year (September 1 to June 1) 37: x; Week of year (September 1 to June 1) 38: x; Week of year (September 1 to June 1) 39: x; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: 2; Week of year (September 1 to June 1) 13: 2; Week of year (September 1 to June 1) 14: 2; Week of year (September 1 to June 1) 15: 2; Week of year (September 1 to June 1) 16: 2; Week of year (September 1 to June 1) 17: 2; Week of year (September 1 to June 1) 18: 2; Week of year (September 1 to June 1) 19: 2; Week of year (September 1 to June 1) 20: 2; Week of year (September 1 to June 1) 21: 2; Week of year (September 1 to June 1) 22: 1; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
4 | MR | 12 | 1 | 1 | 12 | bar: Week of year (September 1 to June 1) 34 to Week of year (September 1 to June 1) 43; Week of year (September 1 to June 1) 12 to Week of year (September 1 to June 1) 25
5&6 | UFSWS-GP | 10 | 1 | 1 | 10 | bar: Week of year (September 1 to June 1) 42 to Week of year (September 1 to June 1) 46; Week of year (September 1 to June 1) 10 to Week of year (September 1 to June 1) 19
7 | SD | 12 | 1 | 1 | 12 | bar: Week of year (September 1 to June 1) 40 to Week of year (September 1 to June 1) 51; Week of year (September 1 to June 1) 1 to Week of year (September 1 to June 1) 17
8 | NE | 15 | 1 | 1 | 15 | bar: Week of year (September 1 to June 1) 40 to Week of year (September 1 to June 1) 47; Week of year (September 1 to June 1) 1 to Week of year (September 1 to June 1) 16
9 | NE | 10 | 1 | 1 | 10 | bar: Week of year (September 1 to June 1) 41 to Week of year (September 1 to June 1) 50; Week of year (September 1 to June 1) 1 to Week of year (September 1 to June 1) 15
9 | MO | 10 | 1 | 1 | 10 | bar: Week of year (September 1 to June 1) 41 to Week of year (September 1 to June 1) 50; Week of year (September 1 to June 1) 1 to Week of year (September 1 to June 1) 15
10 | MO | 10 | 1 | 1 | 10 | bar: Week of year (September 1 to June 1) 40 to Week of year (September 1 to June 1) 50; Week of year (September 1 to June 1) 1 to Week of year (September 1 to June 1) 15
13 | USACE | 11 | 1 | 1 | 11 | bar: Week of year (September 1 to June 1) 42 to Week of year (September 1 to June 1) 51; Week of year (September 1 to June 1) 1 to Week of year (September 1 to June 1) 15
14 | USACE | 14 | 1 | 1 | 14 | bar: Week of year (September 1 to June 1) 43 to Week of year (September 1 to June 1) 15

## 1 crews @ 2 bends per wk
Segment | Group | Bends to sample | Crews | Bends/week | Weeks to complete | Week of year (September 1 to June 1)
[6 empty] | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | MT | 12 | 1 | 2 | 6 | Week of year (September 1 to June 1) 34: 2; Week of year (September 1 to June 1) 35: 2; Week of year (September 1 to June 1) 36: 2; Week of year (September 1 to June 1) 37: 2; Week of year (September 1 to June 1) 38: 2; Week of year (September 1 to June 1) 39: 2; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
3 | MT | 21 | 1 | 2 | 10.5 | Week of year (September 1 to June 1) 34: x; Week of year (September 1 to June 1) 35: x; Week of year (September 1 to June 1) 36: x; Week of year (September 1 to June 1) 37: x; Week of year (September 1 to June 1) 38: x; Week of year (September 1 to June 1) 39: x; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: 1; Week of year (September 1 to June 1) 16: 2; Week of year (September 1 to June 1) 17: 2; Week of year (September 1 to June 1) 18: 2; Week of year (September 1 to June 1) 19: 2; Week of year (September 1 to June 1) 20: 2; Week of year (September 1 to June 1) 21: 2; Week of year (September 1 to June 1) 22: 2; Week of year (September 1 to June 1) 23: 2; Week of year (September 1 to June 1) 24: 2; Week of year (September 1 to June 1) 25: 2
4 | MR | 12 | 1 | 2 | 6 | Week of year (September 1 to June 1) 34: 2; Week of year (September 1 to June 1) 35: 2; Week of year (September 1 to June 1) 36: 2; Week of year (September 1 to June 1) 37: 2; Week of year (September 1 to June 1) 38: 2; Week of year (September 1 to June 1) 39: 2; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: 2; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
5&6 | UFSWS-GP | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x
7 | SD | 12 | 1 | 2 | 6 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | x | x | x | x | x | x |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
8 | NE | 15 | 1 | 2 | 7.5 | Week of year (September 1 to June 1) 40: 2; Week of year (September 1 to June 1) 41: 2; Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 47: 1; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x
9 | NE | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: 2; Week of year (September 1 to June 1) 9: 2; Week of year (September 1 to June 1) 10: 2; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
9 | MO | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: 2; Week of year (September 1 to June 1) 9: 2; Week of year (September 1 to June 1) 10: 2; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
10 | MO | 10 | 1 | 2 | 5 | Week of year (September 1 to June 1) 40: 2; Week of year (September 1 to June 1) 41: 2; Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
13 | USACE | 11 | 1 | 2 | 5.5 | Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 47: 1; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 51: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
14 | USACE | 14 | 1 | 2 | 7 | Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 51: x; Week of year (September 1 to June 1) 52: x; Week of year (September 1 to June 1) 1: 2; Week of year (September 1 to June 1) 2: 2; Week of year (September 1 to June 1) 3: 2; Week of year (September 1 to June 1) 4: 2; Week of year (September 1 to June 1) 5: 2; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x

## 2 crews @ 1 bends per wk
Segment | Group | Bends to sample | Crews | Bends/week | Weeks to complete | Week of year (September 1 to June 1)
[6 empty] | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | MT | 12 | 2 | 1 | 6 | Week of year (September 1 to June 1) 34: 2; Week of year (September 1 to June 1) 35: 2; Week of year (September 1 to June 1) 36: 2; Week of year (September 1 to June 1) 37: 2; Week of year (September 1 to June 1) 38: 2; Week of year (September 1 to June 1) 39: 2; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
3 | MT | 21 | 2 | 1 | 10.5 | Week of year (September 1 to June 1) 34: x; Week of year (September 1 to June 1) 35: x; Week of year (September 1 to June 1) 36: x; Week of year (September 1 to June 1) 37: x; Week of year (September 1 to June 1) 38: x; Week of year (September 1 to June 1) 39: x; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: 2; Week of year (September 1 to June 1) 13: 2; Week of year (September 1 to June 1) 14: 2; Week of year (September 1 to June 1) 15: 2; Week of year (September 1 to June 1) 16: 2; Week of year (September 1 to June 1) 17: 2; Week of year (September 1 to June 1) 18: 2; Week of year (September 1 to June 1) 19: 2; Week of year (September 1 to June 1) 20: 2; Week of year (September 1 to June 1) 21: 2; Week of year (September 1 to June 1) 22: 1; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
4 | MR | 12 | 2 | 1 | 6 | Week of year (September 1 to June 1) 34: 2; Week of year (September 1 to June 1) 35: 2; Week of year (September 1 to June 1) 36: 2; Week of year (September 1 to June 1) 37: 2; Week of year (September 1 to June 1) 38: 2; Week of year (September 1 to June 1) 39: 2; Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x; Week of year (September 1 to June 1) 20: x; Week of year (September 1 to June 1) 21: x; Week of year (September 1 to June 1) 22: x; Week of year (September 1 to June 1) 23: x; Week of year (September 1 to June 1) 24: x; Week of year (September 1 to June 1) 25: x
5&6 | UFSWS-GP | 10 | 2 | 1 | 5 | Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x; Week of year (September 1 to June 1) 17: x; Week of year (September 1 to June 1) 18: x; Week of year (September 1 to June 1) 19: x
7 | SD | 12 | 2 | 1 | 6 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | x | x | x | x | x | x |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
8 | NE | 15 | 2 | 1 | 7.5 | Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 1: 2; Week of year (September 1 to June 1) 2: 2; Week of year (September 1 to June 1) 3: 2; Week of year (September 1 to June 1) 4: 2; Week of year (September 1 to June 1) 5: 2; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: 1; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x; Week of year (September 1 to June 1) 16: x
9 | NE | 10 | 2 | 1 | 5 | Week of year (September 1 to June 1) 41: 2; Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
9 | MO | 10 | 2 | 1 | 5 | Week of year (September 1 to June 1) 41: 2; Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
10 | MO | 10 | 2 | 1 | 5 | Week of year (September 1 to June 1) 40: x; Week of year (September 1 to June 1) 41: x; Week of year (September 1 to June 1) 42: x; Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 1: 2; Week of year (September 1 to June 1) 2: 2; Week of year (September 1 to June 1) 3: 2; Week of year (September 1 to June 1) 4: 2; Week of year (September 1 to June 1) 5: 2; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
13 | USACE | 11 | 2 | 1 | 5.5 | Week of year (September 1 to June 1) 42: 2; Week of year (September 1 to June 1) 43: 2; Week of year (September 1 to June 1) 44: 2; Week of year (September 1 to June 1) 45: 2; Week of year (September 1 to June 1) 46: 2; Week of year (September 1 to June 1) 47: 1; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 51: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: x; Week of year (September 1 to June 1) 3: x; Week of year (September 1 to June 1) 4: x; Week of year (September 1 to June 1) 5: x; Week of year (September 1 to June 1) 6: x; Week of year (September 1 to June 1) 7: x; Week of year (September 1 to June 1) 8: x; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x
14 | USACE | 14 | 2 | 1 | 7 | Week of year (September 1 to June 1) 43: x; Week of year (September 1 to June 1) 44: x; Week of year (September 1 to June 1) 45: x; Week of year (September 1 to June 1) 46: x; Week of year (September 1 to June 1) 47: x; Week of year (September 1 to June 1) 48: x; Week of year (September 1 to June 1) 49: x; Week of year (September 1 to June 1) 50: x; Week of year (September 1 to June 1) 51: x; Week of year (September 1 to June 1) 52: x; Week of year (September 1 to June 1) 1: x; Week of year (September 1 to June 1) 2: 2; Week of year (September 1 to June 1) 3: 2; Week of year (September 1 to June 1) 4: 2; Week of year (September 1 to June 1) 5: 2; Week of year (September 1 to June 1) 6: 2; Week of year (September 1 to June 1) 7: 2; Week of year (September 1 to June 1) 8: 2; Week of year (September 1 to June 1) 9: x; Week of year (September 1 to June 1) 10: x; Week of year (September 1 to June 1) 11: x; Week of year (September 1 to June 1) 12: x; Week of year (September 1 to June 1) 13: x; Week of year (September 1 to June 1) 14: x; Week of year (September 1 to June 1) 15: x